## Gantt Chart - Manual Duration
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form
Read about the project (literature review) | 2023-10-16 | 2023-11-30 | 46 | 36 | 9 | 80%
aims, objectives and proposal | 2023-10-16 | 2023-11-15 | 31 | 30 | 0 | 100%
install software and investigate the platform | 2023-10-30 | 2023-11-17 | 19 | 16.2 | 1.8 | 90%
Lightning Presentation preperation | 2023-11-24 | 2023-12-01 | 8 | 0 | 7 | 0%
Writing interim report | 2023-10-16 | 2024-01-29 | 106 | 0 | 105 | 0%
Interim eport submission | 2024-02-02 | 2024-02-02 | 1 | 0 | 0 | 0%
Implement Machine vision in simulation only | 2023-11-17 | 2023-12-17 | 31 | 0 | 30 | 0%
Start the implementation | 2024-01-31 | 2024-03-11 | 41 | 0 | 40 | 0%
Results collection | 2024-02-20 | 2024-03-11 | 21 | 0 | 20 | 0%
Results analysis | 2024-03-01 | 2024-03-14 | 14 | 0 | 13 | 0%
Writing report | 2023-10-16 | 2024-05-11 | 209 | 0 | 208 | 0%
Report submission | 2024-05-10 | 2024-05-10 | 1 | 0 | 0 | 0%
Formulas:
Start Date = [Start Date, row above]+75
End Date = [Start Date]+45