## Gantt Chart - Manual Duration
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form
Read about the project (literature review) | 2023-11-14 | 2023-12-14 | 31 | 31 | 0 | 100%
Select an appropriate type of needed sensors | 2023-12-15 | 2023-12-28 | 14 | 14 | 0 | 100%
Design a circuit diagram | 2023-12-29 | 2024-01-11 | 14 | 14 | 0 | 100%
Develop a communication protocol | 2024-01-12 | 2024-01-25 | 14 | 2.6 | 10.4 | 20%
Implement a wireless protocol | 2024-01-26 | 2024-02-15 | 21 | 0 | 20 | 0%
Write code for the sensors | 2024-02-16 | 2024-03-07 | 21 | 0 | 20 | 0%
Develop a GUI application through Open Ephys GUI | 2024-03-08 | 2024-03-28 | 21 | 0 | 20 | 0%
Writing the paper | 2024-03-29 | 2024-04-18 | 21 | 0 | 20 | 0%
Preparing for the presentation | 2024-04-19 | 2024-05-10 | 22 | 0 | 21 | 0%
Presentation and report submission | 2023-11-14 | 2024-05-10 | 179 | 64.08 | 113.92 | 36%
|  | 64 |  | 0.35754
Formulas:
Start Date = [End Date, row above]+1
End Date = [Start Date]+30
End Date = [End Date, row above]